## Overview
Year | Focus | Key Deliverables
2025 | Foundation | MAS-Sandbox, GEORGE MVP, 5 Core Agents
2026 | Showcase | CES 2026 Launch, virtauto.OS MVP
2027 | Expansion | Support EDAG/VW Transformation, 3D-Printed Car PoC
2028 | Scaling | MAS-as-a-Service, North America Entry
2029 | Ecosystem | Full Fusion Strategy Ecosystem
2030 | Global Impact | virtauto as Digital Brain for OEMs

## Phases
Phase | Focus | Deliverables | Duration
0 | Finalize Architecture | Agent Map, Fusion Strategy Blueprint | Q1-Q2 2025
1 | Build Core Agents | Root Cause, Procurement, Supply Chain, Quality, Finance Agents | Q3-Q4 2025
2 | Integrate & Orchestrate | GEORGE Orchestrator, MAS Sandbox Live | 2026
3 | Scale & Refine | Deployment in OEM environment, Continuous Iteration | 2027–2030

## Milestones
Year | Milestone | Owner
2025 | MAS Sandbox with 4–6 Agents | Dev Team
2025 | GEORGE MVP | Architect
2026 | CES 2026 Showcase | Marketing
2026 | virtauto.OS MVP | Engineering
2027 | Support EDAG/VW Transformation | Executive Team
2028 | Launch MAS-as-a-Service | Cloud Ops
2029 | Fusion Strategy Ecosystem live | All Agents
2030 | Global recognition as Digital Brain | Board

## Dependencies
Task | Depends On | Risk
Build Core Agents | Finalize Architecture | Delay in prompt engineering
Develop GEORGE Orchestrator | Core Agents | Integration issues
Launch virtauto.OS MVP | GEORGE Orchestrator | Scalability challenges
CES 2026 Showcase | GEORGE + virtauto.OS MVP | Event readiness
MAS-as-a-Service | CES Showcase + OEM Integration | Cloud adoption